## Sheet1
No. | Date of Meeting | Presenting Department | Direction/ | Topic | Action Item | Type | Priority | User Update | PIC | Target Date | Status | Remarks
Recommendation From
1 | 2026-02-16 | HSSE |  | HSSE Update | Swing rope need input from Operation Team |  |  | Will be presented on 26 Feb 26 | Operation |  | CLOSED
2 | 2026-02-16 | HSSE |  | HSSE Update | Presentation for personnel transfer option |  |  | Presented on 26 Feb 2026. | HSSE |  | CLOSED
3 | 2026-02-16 | 4M |  | Operation & Maintenance Update | Arrange meeting on Wednesday or end of this week for finding at MAC |  |  |  | 4M | 2026-02-20 | Open | Overdue
4 | 2026-02-16 |  |  | Operation & Maintenance Update | Meeting for Well Integrity and BD-A3 this week or next week |  |  | Meeting has been held on 3 March 2026 & facilitated by DCWI. | 4M, BD | 2026-02-27 | CLOSED | Overdue
5 | 2026-02-16 | Project |  | Project and E&AI | FID MDK target ==> Q1 |  |  | FID approval should be obtained in (by the end of) Q2 2026 | Project | Q2 2026 | Open
6 | 2026-02-16 | Subsurface |  | Development Update | MoM TCM/OCM finalization |  |  | On review by Related Executives (Ibu Hanna, Pak Suryo, and Pak Kian) | Subsurface | W2 March 26 | Open | Overdue
7 | 2026-02-16 | BD |  | FPSO Contract: Follow Up Post-Meeting with AGN | Internal meeting with BD, 4M, B&R, C&P and Procurement |  |  | Have conducted internal meeting related to FPSO Contract Extension Update on 4 March. | BD | 2026-03-05 | CLOSED
8 | 2026-02-16 |  |  | Other | Make sure SMSDL & Ratu position ==> confirmation or guideline from ManCom Secretary & Legal Department |  |  | RATU will become the new ultimate beneficiary of the SMSDL. NO changes on SMSDL as 20% of HCML shareholders. | ManCom Secretary |  | CLOSED
9 | 2026-02-23 | HSSE | Way | Navy Training Area | Please coordinate with Navy and if necessary with MLBS Team as at the beginning, the agreement is to replace the existing navy practice area with new area provides by HCML-SKK Migas thru cost recovery mechanism. |  |  | * HSSE (with support from MLBS and Operation Team) have been conducting a series of meetings with the Indonesian Navy and SKK Migas to draft a new Cooperation Agreement (PKS - Perjanjian Kerjasam) regarding the Joint Use of the South of Raas Island Navy Exercise Area for HCML gas production facilties. | HSSE - Security | End of March 2026 | Open | Current update: Still under further discussion, particularly concerning the mechanism for providing fuel support for maritime security patrols.
[8 empty] | * There will be no cost associated with this Cooperation Agreement for the joint use of the Navy exercise area. However, SKK Migas has requested HCML, together with Petronas, to establish a separate Cooperation Agreement related to offshore security arrangements, which is currently in the finalization stage. |  |  |  | The next meeting (SKK Migas, The Navy HQ, HCML and Petronas) will be conducted on 29 April 2026
Update 06 May 2026:
MoU draft finalization meeting by 6 May 2026 ==> Discussion with SKK Migas, TNI-AL and Petronas are ongoing, with a particular focus on establishing the appropriate mechanism for providing fuel support to maritime security patrol operations under a farm-in contractual arrangement with Petronas.
Need support from Logistic. The MoU (PKS) signing is scheduled to be conducted during the Security Coordination Meeting with TNI in July 2026.
10 | 2026-02-23 | 4M | Way | Production Operations - 4M | Include a review of the rights and obligations of the parties regarding the FPU downtime. Due to the contractor’s technical issues (blackout), HCML has incurred/suffered with commercial consequences. Please also review for other production facilities. |  |  |  | 4M | Q1 2026 | Open
11 | 2026-02-23 | Project | Way | MDK Project Update | Project to be put after HSSE on the sequesnce in Weekly Staff Meeting. Presented in one session with DCWI and Marketing. |  |  |  | Project | TBA | Closed | Maintain existing cadence
12 | 2026-02-23 | Project | Way | MDK Project Update | Arrange a coordination meeting on MDK Project (MDK Mode: Go) among related departments (Project, DCWI, Marketing, Engineering, C&P, Subsurface, Procurement) |  |  |  | Project | W1 March 2026 | Open | Wait for formal comencement statement from HCML Management
13 | 2026-02-23 | E&AI | SB | Engineering Update | Power Generation to be presented in the upcoming Weekly Staff Meeting |  |  |  | E&AI | 2026-03-02 | Open
14 | 2026-02-23 | DCWI | SB | MDK and BD Drilling | Prepare pro and cons on infill and intervention wells (infil+intervention or 2 infill, etc.) for BD to be propossed to HCML Management. |  |  | DCWI presented the Jack‑Up Rig Drilling Strategy on 6 April 2026, covering the following four scenarios: | DCWI | TBA | CLOSED
Scenario 1: MDK development wells combined with BD infill well and BD well intervention
Scenario 2: MDK development wells combined with BD infill well, BD well intervention, and exploration well(s)
Scenario 3: MDK development wells executed separately from BD infill well and BD well intervention
Scenario 4: MD development wells combined with exploration well(s), but executed separately from BD infill well and BD well intervention
The meeting resulted in a recommendation to expedite the BD infill well plan.
If the BD infill well can be combined with MDK development wells, this would be preferable; however, if this is not feasible, proceeding separately will require further discussion with SKK Migas to help with jack up drilling rig strategy.
As follow up, DCWI in collaboration with Subsurface Department preparing BD infill well Mancom Resolution with the objective of proceeding with technical discussions with SKK Migas, as well as continuing the tender process for drilling long lead items and jack up rig services for the BD infill well.
15 | 2026-02-23 | DCWI | SB/Way | MDK and BD Drilling | Drilling timeline better to be discussed with other related departments by focusing to MDK first, and later to BD. Present the result in the upcoming Weekly Staff Meeting (special topics) |  |  | DCWI has initiated MDK Coordination Meetings with the relevant departments on 30 March 2026 and 16 April 2026, during which the required reference data were shared. | DCWI | TBA | CLOSED
Daily close coordination among the teams is ongoing.
16 | 2026-03-02 | PBR | WKF | Safety Moment | Encourage Presenting Department to deliver Safety Moment close to our life. |  |  | - | All Departments | - | -
17 | 2026-03-02 | HSSE | SB | HSSE Update | Due to many Influenza Type -A cases recently, HSSE need to conduct socialization to all employees and especially to personnel before going offshore (when in SSB/STP) to prevent any outbreak in the operating Area. |  |  | Action plan being developed, focus on preventive measures including: | HSSE | 1. HSSE Alert Blast: 06 Mar 2026 | CLOSED
1. Health awareness through HSSE Alert blast (Target 6 March)
2. Strengthening health check & screening during crew change and body temperature check in Jakarta & Surabaya Office
[8 empty] | 3. Influenza Vaccination Program (Target end of April 2026) |  | 1. Influenza Vaccination Program: End of April 2026 | CLOSED | Current update: The vaccination will be held on 22 April 2026 at Jakarta Office
18 | 2026-03-02 | HSSE | WKF | HSSE Update | HSSE need to update OSCP meeting result to Pak Wang Kaifei |  |  | Already updated on 02 Mar 2026 | HSSE | 2026-03-03 | CLOSED
19 | 2026-03-02 | Operations | SB | Operation | Further discussion on budget allocation on unbundling program from Operations |  |  |  | Operations + B&R |  | Open
20 | 2026-03-02 | Engineering & Project | WKF | E&AI | Arrange a Meeting for Power Generator Issue among related departments |  |  | Presented on 02 Mar 2026 | E&AI | 2026-03-06 | CLOSED
21 | 2026-03-02 | DCWI | SB | Well Intervention | This week, operations team will conduct Risk Assessment on BD-A1 well logging activities. Please DCWI to coordinate with HSSE Team as we need to prapare a case. |  |  | * DCWI has conducted several meetings with HSSE, Prod. BD, and other related departments to discuss the risk assessment. | DCWI | 2026-03-06 | CLOSED
* A formal meeting is scheduled for 1-2 April 2026, regarding BD-A1st logging TRA and operation discussion.
22 | 2026-03-02 | Subsurface | WKF | Special: MAC Production Rate | Production and B&R Team to re-calculate the production number with 33 MMSCFD of sales from MAC |  |  |  | Production 4M and B&R | 2026-03-06 | Open
23 | 2026-03-02 | Subsurface | WKF | Special: MAC Production Rate | C&P to re-calculate which is the better production rate for HCML on MAC if the THP keep declining? -- Recalculate all the economics for each well for the rest of MAC life. |  |  | MAC Production rate economic evaluation has been shared during staff meeting on 30 Mar 2026 (special topic) together with Subsurface. | C&P | 2026-03-06 | CLOSED
24 | 2026-03-02 | Subsurface | WKF | Special: MAC Production Rate | Prepare Decision Tree on what's next after 3 Months of pressure test |  |  |  | Subsurface and C&P | W1 June 2026 | Open
25 | 2026-03-02 | Subsurface | WKF | Special: MAC Production Rate | Present a more detailed scenarios in 3 weeks. |  |  | Presented on 30 March 2026 | Subsurface | 2026-03-30 | CLOSED
26 | 2026-03-02 | 4M | WKF | Special: SBNP (Navigation Buoy) | SoW better to be complete, and we can use BD as reference. Please present it to Shareholders during ManCom Meeting. |  |  |  | 4M | 2026-03-04 | CLOSED | Will be presented during ManCom Meeting.
27 | 2026-03-09 | Marketing | WKF | 2M Gas Allocation | Provide translation on 2M Gas allocation from MEMR to GM |  |  |  | Marketing | 2026-03-09 | CLOSED | Translation has been provided & sent through CITRA Application on 09 Mar 2026.
28 | 2026-03-09 | Logistics | WKF | Fuel for Vessels | Discuss on Fuel Budget forecast with GM on 10 March 2026, 08:30 AM. Need to present the simulation and mitigation on increase fuel price |  |  | Meeting has been held on 10 March 2026. |  | 2026-03-10 | CLOSED
29 | 2026-03-09 | Production | WKF | Production Operations | Provide forecast scenarios for Production outlook: |  |  |  |  | 2026-03-09 | Open
- BD: 53 MM
- 2M: use two scenarios (with and without engine exchange)
Provide the forecast to B&R Team
30 | 2026-03-16 | Marketing | WKF | Gas Marketing--IAE Issue | New IAE's investor should conduct DD to IAE, and HCML should also conduct DD to IAE after new investor join-in. Before continue business with HCML, IAE need to clean up all of their liabilities. |  |  |  | Marketing, Legal, Finance |  | Open
31 | 2026-03-16 | Marketing | WKF | Gas Marketing--TOP | All TOP contractual should follow the regulation. Finance shall monitor this TOP implementation and TOP should be related to the buyer's SBLC. |  |  |  | Marketing, C&P, Legal, Finance |  | Open
32 | 2026-03-16 | HSSE | WKF | Special Topics on OSRE | Provide complete information to GM in a more detailed. (quantity, location, usage, contract terms, yearly rental cost, etc.) |  |  | Has been sent to Pak WKF on 31 March 2026 | HSSE, Logistics, Productions | 2026-03-31 | CLOSED
- How about OSRE equipment if the oil spill impacted to other PSC?
- How if the oil spill impacted to the surrounding island/shore and what is the responsibility carried by other PSCs.
33 | 2026-03-30 | HSSE | WKF & SB | HSSE Update - Road Blockage | Due to the security matters in GMS, ensure if emergency happen we can safely evacuate; Prepare well-accessible alternative evacuation routes, ensure adequate lighting, and improve road conditions; and update the emergency procedure in written and conduct a drill |  |  | Has been updated to consider road access blockage scenarios. | HSSE, Logistics, Productions |  | CLOSED
Current update: routing for approval
34 | 2026-03-30 | Logistics | SB | Logistic Update | Prepare information on how much fuel consumption during condensate lifting |  |  |  | Logistic |  | Open
35 | 2026-03-30 | Project | SB | Project Update | -. Need to update flow assurance study |  |  |  | E&AI, Production |  | Open
-. From production team: will conduct GTC high rate performance test
36 | 2026-03-30 | Subsurface | WKF | Special Topic - MAC Field Production Performance | Prepare simulation for the production between 17-22 MM, to find the better maximum production rate. Recommend to start at 19 MM for 3 weeks & evaluate the other 2 wells |  |  |  | Subsurface |  | Open
37 | 2026-03-30 | Subsurface | WKF | Special Topic - MAC Field Production Performance | -. E&AI to ensure the stability of the facilities |  |  |  | E&AI, Marketing |  | Open
-. Marketing to ensure all the gas can be absorb by the gas buyer
38 | 2026-03-30 |  | WKF | Other | Follow up on MDK Incentive |  |  |  | C&P |  | Open
39 | 2026-03-30 |  | WKF | Other | Follow up on 2 Cenovus Audit pending with HR & Operation team |  |  |  | IAC, HRGA, Operation |  | Open
40 | 2026-03-30 |  | WKF | Other | Distribute the questions from last ManCom meeting to all related department & collect all the answer early next week for review |  |  |  | ManCom Secretary | 2026-04-06 | Open
41 | 2026-03-30 | HSSE | WKF | HSSE | Reinforce Awareness to the Vessel Company regarding the Domestic Waste Burning Activity happened on Limin ASD 43 Deck |  |  | Done during investigation Limin and through email to another vessel. | Logistics & HSSE |  | CLOSED
42 | 2026-04-06 | Marketing | WKF | Safety Moment | Assess the necessary action to fix employees' posture during working hour by looking into desk extension equipment to make the employee able to work while standing. |  |  |  | HSSE and HRGA
43 | 2026-04-06 | HSSE | WKF | HSSE Update | Study on unauthorized access to HCML Operating Area to prevent the similar issues happened in the future. |  |  | Drone study: Study report DONE and has been sent to GM. | HSSE | W3 May 2026 | Open | Action plan has been developed and shared to Pak Xiang Ming.
[8 empty] | Next plan: to prepare action plans including benchmark to PHM. |  |  |  | Update: Technical meeting with Cenertech to be done by 6 May 2026. Benchmark PHM will be done on W3-2026.
Update 29 May 2026: Online benchmark with PHM done on 26 May. Onsite benchmarking will do around W4 June (waiting for PHM confirmation)
44 | 2026-04-06 | Operation | SB | Operation Update | Need suggestion from DCWI & Subsurface for ramp-up scenario, and before every ramp-up will inspect the basket strainer |  |  |  | Operation, DCWI, Subsurface |  | Open
45 | 2026-04-06 | Operation | SB | Operation Update | Operation and Subsurface need to work closely to find the cause for the sand and debris, then make suggestion for the production rate. |  |  |  | Operation, Subsurface |  | Open
46 | 2026-04-06 | Marketing | WKF | Marketing Update | Marketing Team to finalize the Amendment of 2M GSA so that HCML can use the new price starting on 1 January 2026. |  |  | HCML told PKG that HCML will reduce the volume and allocate to other buyers (refer to 2nd Amendment) | Marketing
47 | 2026-04-06 | Marketing | WKF | Marketing Update | Finance to Coordinate with Marketing Team to check for any missing SBLC for the benefit of HCML |  |  |  | Marketing
48 | 2026-04-06 | Marketing | WKF | Sustainability | C&P Team to followup the incentive on MDK project as it is still pending approval from SKK. Shareholders will not further invest on new fields without PSC Extension. |  |  |  | PSC Extension Team (C&P and Subsurface)
49 | 2026-04-06 | Marketing | WKF | SKK Migas Pending Approval | JCAP to list down all pending approval from SKK Migas regarding the sustainability of HCML business. |  |  | Email has been sent to related Department on 07 April 2026 | JCAP |  | On Progress
50 | 2026-04-06 | Logistics | WKF | Logistics Update | Seek for any formal options to procure fuel for vessels operations outside Pertamina since they cannot yet confirm their fuel availability. |  |  |  | Logistics
51 | 2026-04-06 | Logistics | WKF | Logistics Update | On 20% increase on fuel price: conduct operations efficiency and discuss the additional fuel budget with Shareholders and SKK Migas. |  |  |  | Logistics | 2026-04-10 | CLOSED
52 | 2026-04-06 | Logistics | WKF | Logistics Update | Postponed condensate lifting on May to efficient the vessels operations. |  |  | C&P and Losgistics Team will present this matter during ManCom Meeting. | Logistics | 2026-04-10 | CLOSED
53 | 2026-04-06 | E&AI | WKF | E&AI | Power Generatior: Ensure that the sparepart is 100% available and reliable for us to decide on whether we need to replace the power generation or not. If the sparepart is available and reliable, we do not need the replacement. |  |  | Maintenance and E&AI will have a meeting with the vendor from Malaysia to ensure the matter. The sparepart is stock on hand, not a newly manufactured. | Maintenance and E&AI |  | CLOSED
54 | 2026-04-06 | E&AI | WKF | E&AI | Arrange a meeting on power generation changes from GTG to MTG for MDK field WHP. |  |  | Will arrange between 13-17 April 2026. | E&AI | Next Week
55 | 2026-04-06 | B&R | JnP/WKF | Financial Performance | All departments need to take action for cost efficiency. Maximum of 90% budget utilization is a must. |  |  |  | All Departments | Pictured in Monthly Financial Review by B&R | Open until EoY
56 | 2026-04-13 | HSSE | YS/WKF | HSSE Update | - "Touching" the MOPU leg is serious incident. Need to ensure similar event do not occur again. | Instruction |  | Logistics and HSSE will conduct investigation on this issue. Happeneed due to engine problem of ub peregrine. | HSSE and Logistics |  | CLOSED
- should be a procedure to maintain distance of vessel with our facilities.
- to complete the investigation report to find the root cause.
57 | 2026-04-13 | Operations | WKF/SB | Lifting Operations | Talk with SKK if they can postpone lifting in April by 10 days and also reducing number of lifting within this year. | Advise |  |  | C&P and Prod. BD | Present on next week's Weekly Staff Meeting | CLOSED
58 | 2026-04-13 | Operations | WKF | MDA Power Generation | Arrange a meeting with GM on Tuesday, 2PM on MDA Power Generation. |  |  | Invitation sent by secretary | E&AI | 2026-04-14 | CLOSED
59 | 2026-04-13 | Operations | WKF | Sand issues in HCML Fields. | - Increase frequenscy of sampling by SMTF. Update to GM every 2 Weeks. |  |  |  | SMTF (Subsurface, DCWI, Operations) | First Update on 27 April 2026
Comprehensive solution for sand issue.
- Propose best production rate.
60 | 2026-04-13 | Logistics | WKF | Fuel Contract | Send all history of Fuel Contract Amendment to GM including the reasons/justification, and changes of the article. |  |  |  | Logistics and Procurement | by 17 April 2026
61 | 2026-04-13 | Engineering & Project | WKF | Followup Meeting | Arrange a meeting on BD WHP subsidence |  |  | Meeting conducted on 15 April 2026 | E&AI |  | CLOSED
62 | 2026-04-13 | Development | WKF | Subsurface | Consult with Head Office (research Center--Shanghai and Shenzen) on sand issues in MAC to find the root cause of the MAC sand issue | Advise |  |  | Wang Jimei and Xiang Ming
63 | 2026-04-13 | - | JnP | Invoice Payment/Finance | -All Department should maintain 90% of 2026 Budget |  |  |  | FAT | N/A
- Invoice Settlement suporting documents is not complete. Ensure the completeness and accuracy of the invoice, including but not limited to: Bank Account
64 | 2026-04-13 | Relations | WKF | Special Topics - Road Blockage | - We shall categorize the other road as "Backup Road" instead of "Alternative Road" only for Daily Supply vehichle (light vehicle). |  |  |  | ROR/Legal
- Ensure the backup road owned 100% by the owner (H. Khoiron).
- Conduct Feasibility Study (civil works, including the cost) to evaluate the backup road to be used for operational road (including heavy truct to pass the road).
65 | 2026-04-13 | E&AI | WKF | Special Topics - Underwater Inspection | - Ensure no conflicting date between HCML and Kangean schedule in using/executing the contract. |  |  | - HCML will execute the contract first, later Kangean. | E&AI, BP&T
- All certificates are under user. Ensure these certificates are well monitored. or centralized. To develop centralized certificate monitoring System.
66 | 2026-04-20 | HSSE | WKF | Peregrin touch MOPU Leg | - Need to send formal warning letter to person responsible. |  | MEDIUM | 1. Warning letter to vessel owner DONE. | HSSE/Logistics | 2026-04-30 | Open
[5 empty] | - Disseminate the procedure to vessel captain during lifting operations. |  |  | 2. Vessel captain competency review will be done in June.
67 | 2026-04-20 | HSSE |  | Peregrin touch MOPU Leg | Recommendation for Action Plan: |  | HIGH | SOP vessel approach MOPU in approval routing. | HSSE, Operation, Logistic | End of May 2026 | Open
-. Conduct immediate safety stand-down accross all vessels & MOPU
-. Strengthening communication protocol in TRA/ Procedures
-. Positioning Control enhancement
68 | 2026-04-20 | Marketing | WKF | Marketing Update | IAE TOP Makeup Gas: | Instruction | HIGH | Will schedule separate meeting to discuss further | FAT/Marketing
- How much TOP they paid to HCML
- Provide recommendation to GM (makeup or refund)
69 | 2026-04-20 |  | JnP | Finance | FAT, B&R, and BPT work together to improve local SAP and take the system more efficient and friendly. | Advise |  |  | BPT/FAT/B&R
70 | 2026-04-20 |  | WKF | DCWI | Prepare BD Decison tree for the Well Intervention | Instruction | MEDIUM | -. DCWI has completed the BD-A1ST forward plan and decision tree that shown on the staff meeting special topic on 27 April 2026. | DCWI | 2026-04-30 | CLOSED | - DCWI has completed the BD-A1ST and BD-A4 forward plan and decision tree that shown on the staff meeting special topic on 27 April 2026.
[8 empty] | -. Regarding the BD-A4 the draft of forward plan & decision tree completed. |  |  |  | -. DCWI and Subsurface have a meeting discussed the BD well forward plan and decision tree early April.
71 | 2026-04-20 |  | WKF | Subsurface | Accelerate study on Geomechanics |  |  |  | Subsurface
72 | 2026-04-27 | Operations | WKF | MAC-A2 Well | To expedite the MAC-A2 desander installation |  | HIGH |  | E&AI/Production 4M
73 | 2026-04-27 | Engineering & Project | WKF | MDK Project Update | Please be careful when sharing documents with ex-employees currently work with other company, such as Timas--one of the bidder for MDK Project |  | MEDIUM |  | Project
74 | 2026-04-27 | Development | KH | Subsurface | Subsurface to make a special slides to monitor/focus on MAC-A2 and presented during the Weekly Staff Meeting | Instruction | MEDIUM |  | Subsurface | 2026-05-04 | Open
75 | 2026-04-27 | General | JnP/WKF | General | All departments to revisit their own procedure and make update/adjustment (if any) | Advise | LOW |  | All Departments
76 | 2026-04-27 | Marketing | WKF | Special Topics on IAE GSA Termination | - C&P, Finance, Legal, Marketing, and IAC to review all 3 (three) options for IAE GSA Termination. Each department to provide the assessment and recommendation from their own perspective. | Instruction | HIGH | - Legal will provide the written legal opinion | C&P, Finance, Legal, Marketing, and IAC | 2026-04-30 | Open
[5 empty] | - Provide legal opinion in written to GM. |  |  | - Marketing will negotiate with IAE
- Marketing to negotiate with IAE to set a possible waiver for all parties to leave the GSA peacefully.
77 | 2026-04-27 | Marketing/ Operations | WKF | Special Topics on H2S in BD Pipeline | - HCML to discuss with Pertagas to raise the issue with the gas buyers. If they require to improve the gas specification, the gas buyers may discuss with HCML. | Advise | HIGH |  | Marketing, Production BD, and E&AI
- Production BD and E&AI to ensure if the issue is scientifically and technically correct in finding the root cause.
78 | 2026-04-27 | Production BD and DCWI | WKF/SB/KH | Special Topics on BD-A1ST Well Logging | - Use downhole camera to understand the blockage (disgnostic). | Advise | HIGH | - Perform a downhole camera survey to identify the restriction (feasible window is aroun Aug 2026, during good weather window based on previous experience of weather condition in BD) | Production BD, DCWI, and Subsurface |  | In process
[5 empty] | - Use available time window on August to do the activities. DCWI to provide tentative timeline. |  |  | -. The 2nd RIH DHCam operation plan for BD-A1ST has completed and with meeting discussion with Subsurface as well.
- If the issue is on tubing deformation, we need to shut in the well immediately.
- DCWI to compare cost scenarios (including the mob and demob).
79 | 2026-05-04 | HSSE | SB/JnP | HSSE Update | - On using drone to prevent fishermen entering our premises offshore, HSSE Team to consult with ROR on this matter, especially on the community relationship. | Advise | HIGH | Oil spill during condensate lifting: Investigation has been DONE 3 May and wait for final report of investigation. | HSSE |  | CLOSED | Incident investigation of condensate sheen in BD has been done and the report now in routing for approval.
- On oil spill issue, HSSE, Production, and C&P to conduct the investigation to ensure it is not happened again in the next lifting by improving the procedure and mitigate the risk.
Update 29 May: Investigation has been done on 3 May and wait for final report of investigation ==> Investigation report has been approved.
80 | 2026-05-11 | Operations | SB | 2M TAR | 2M TAR from WHP a bit lagging from planned schedule. HCML May only conduct prioritized tasks. | Advise | HIGH |  | Prod 4M and Maintenance
81 | 2026-05-11 | Operations | SB/JnP | MOPU | - Proposed to investigate the LIL leak in MOPU. Since there should be notrogen blanket to prevent the leak. | Advise | HIGH |  | HSSE/Production 4M
- Please enhanve the facility monitoring in our operations area.
82 | 2026-05-11 | DCWI | HR | MDK Drilling Plan | DCWI better to keep drilling spud-in date for MDK Project rather than adjusted along with the EPCI tender dynamic processes. | Advise | MEDIUM | Drilling Spud In: 28 Dec 2027. | DCWI |  | In process
(based on 2nd timeline adjustment from MDK Project on 07 May 2026)
83 | 2026-05-25 | Logistics | SB | Logistics Update | Need to check MH-7 Preventive Maintenance | Advise | HIGH | Already conducted. | Logistics |  | Closed
84 | 2026-05-25 | Project | SB/Way | MDK Project Update | Arrange a meeting internally inviting HCML Management and Procurement to assess the overall project schedule due to delayed bid submission approval from SKK Migas. | Instruction | HIGH | had a meeting with management and related departmenton June 5th. | Project/Procurement | Max. 29 May 26
85 | 2026-05-25 | DCWI | SB/KH |  | MAC Jackup Rig study to be processed without needing ManCom Resolution and can use existing budget. Technical discussion and approval with SKK Migas is in progress. | Instruction | MEDIUM |  | DCWi
86 | 2026-05-25 | HSSE | JnP/SB | General | How many similar problem occurred since the beginning. HSSE to prepare the database on this matters. | Instruction | HIGH | HCML has already the databased in Lotus Notes and still scaterred and difficult to track. | HSSE/BPT
87
88
89
90
91
92
93
94
95
96